## Product Backlog
Epic | User Story | Priority | Status
Module 1: Data Aggregation and Competitor Analysis Engine | As a business analyst, I want to gather competitor data from e-commerce sites so that I can analyze market trends. | High | Done
Module 2: Predictive Modeling for Strategy Adjustments | As a data scientist, I want to build predictive models to forecast competitor pricing and promotions. | High | Done
Module 3: Sentiment Analysis System | As a marketing analyst, I want to analyze customer sentiment to detect shifts in brand perception. | Medium | Done
Module 4: Visualization and Dashboard Development | As a manager, I want to visualize competitor trends and model predictions in an interactive dashboard. | Medium | Done
Module 5: Deployment and Monitoring | As a devops engineer, I want to deploy and monitor the model API for consistent performance. | High | In Progress

## Sprint Backlog
Sprint Goal | Tasks | Owner | Progress
Develop data ingestion pipeline for competitor data | Implement web scraping tools; create schemas; ingest data into structured CSVs/DB | Data Engineer | Completed
Implement feature engineering and predictive modeling | Engineer time-based features (lags, rolling means); train LightGBM regression and classification models | ML Engineer | Completed
Build sentiment analysis engine using LLMs | Integrate sentiment analysis pipeline with Llama/GPT; perform prompt engineering and testing | AI Engineer | Completed
Create Streamlit dashboard and FastAPI deployment | Develop Streamlit dashboard; integrate API; test, document, and deploy models | Full Stack Dev | In Progress

## Daily Stand-up
Yesterday’s Work | Today’s Plan | Blockers
Set up data ingestion environment and collected initial data. | Enhance scraping pipeline and automate ingestion. | Minor data inconsistencies during scraping.
Implemented rag and rolling feature engineering. | Refine feature creation and add promotional signals. | Lag feature alignment for time-series groups.
Created and tested LLM-based sentiment analysis function. | Optimize sentiment prompts and fine-tune model parameters. | LLM output formatting validation (JSON structure).
Developed Streamlit prototype and integrated data visualization. | Enhance Streamlit UI/UX and connect to backend API. | Streamlit performance optimization.
Added FastAPI model prediction API and tested endpoints. | Prepare final documentation, PPT, and GitHub updates. | Pending security review for API deployment.

## Sprint Retrospective
What Went Well | What Could Be Improved | Action Items
Successful integration of data pipeline and feature engineering. | Scraping coverage and automation speed. | Add CI/CD for ingestion and training pipelines.
Effective collaboration between data and AI teams. | Model drift monitoring and retraining triggers. | Enhance monitoring dashboards and data alerts.
Prompt engineering improved LLM sentiment accuracy. | Documentation of prompt templates and examples. | Refine prompt documentation with version control.
Streamlit and FastAPI integration worked smoothly. | API security and deployment automation. | Implement API key management and environment configs.